## 17-239
Task Name | Estimate time (hour) | Take by | Actual Time | Status | Date Doing | Complete Process | Note
[Review 01] Object and problems of project definition | 1 | Tran Hoang Tam | 1 | Done | 15/3/2020
[Review 01] Functional requirements definition | 0.5 | Tran Hoang Tam | 0.5 | Done | 15/3/2020
Learning Angular | 30 | Tran Hoang Tam | 24 | Done | 15/3/2020
Learning Basic .NET Core | 4 | Tran Hoang Tam | 4 | Done | 20/3/2020
Learning Basic Entity Framework | 1 | Tran Hoang Tam | 1 | Done | 20/3/2020
[Review 02] Database's Tables Design | 0.1 | Tran Hoang Tam | 0.1 | Done | 21/3/2020
[Review 02] Table Relationship Diagram Design | 0.05 | Tran Hoang Tam | 0.05 | Done | 21/3/2020
Angular, .NET Core and Entity Framework Environment Setup | 0.1 | Tran Hoang Tam | 0.1 | Done | 22/3/2020
Model and DbContext for Entity Framework | 0.1 | Tran Hoang Tam | 0.1 | Done | 22/3/2020
Controllers for User, Product and Category | 1 | Tran Hoang Tam | 1 | Done | 22/3/2020
CORS (Cross-origin resource sharing) Setup | 0.6 | Tran Hoang Tam | 0.6 | Done | 22/3/2020
Authentication for Login Setup | 1 | Tran Hoang Tam | 1.5 | Done | 23/3/2020
Test Created APIs with Postman | 0.5 | Tran Hoang Tam | 0.5 | Done | 23/3/2020
Necessary External NPM Packages Installing | 0.1 | Tran Hoang Tam | 0.1 | Done | 23/3/2020
User, Product and Category Models | 0.2 | Tran Hoang Tam | 0.2 | Done | 23/3/2020
User, Product and Category Services | 1.5 | Tran Hoang Tam | 1.5 | Done | 23/3/2020
Request Sending with Image Intergration | 1 | Tran Hoang Tam | 6 | Failed | 24/3/2020
Shared Modules (Material Module) | 0.2 | Tran Hoang Tam | 0.2 | Done | 25/3/2020
Login Component for User | 1 | Tran Hoang Tam | 3 | Done | 25/3/2020
Home Component | 2.5 | Tran Hoang Tam | 2.5 | Done | 26/3/2020
Navbar Component | 0.5 | Tran Hoang Tam | 0.5 | Done | 26/3/2020
Sidebar Component | 0.5 | Tran Hoang Tam | 0.5 | Done | 27/3/2020
Spinner Component | 0.2 | Tran Hoang Tam | 0.2 | Done | 27/3/2020
Page Not Found Component | 0.2 | Tran Hoang Tam | 0.2 | Done | 27/3/2020
Product Components (Product List, Product Creating, Product Editting, Product Detail) | 6 | Tran Hoang Tam | 6 | Done | 28/3/2020
Product Modules (Main Module, Routing Module) | 1 | Tran Hoang Tam | 1 | Done | 30/3/2020
Category Component | 1.5 | Tran Hoang Tam | 1.5 | Done | 31/3/2020
Category Modules (Main Module, Routing Module) | 0.5 | Tran Hoang Tam | 0.5 | Done | 31/3/2020
Guards (Authentication Guard, Login Guard) | 1 | Tran Hoang Tam | 1 | Done | 31/3/2020
App Modules (Main Module, Routing Module) | 0.5 | Tran Hoang Tam | 0.5 | Done | 2020-01-04
Boot Controller Creating and Main.ts Configuration | 1 | Tran Hoang Tam | 1 | Done | 2020-01-04
[Review 01] Development Environment Introducing | 0.2 | Tran Hoang Tam | 0.2 | Done | 2020-02-04
[Review 02] Use Case Diagram Design | 0.5 | Tran Hoang Tam | 0.5 | Done | 2020-02-04
[Review 02] Use Case Description | 1.5 | Tran Hoang Tam | 1.5 | Done | 2020-02-04
[Review 02] Class Diagram Design | 0.6 | Tran Hoang Tam | 0.6 | Done | 2020-02-04
[Review 02] ERD (Entity Relationship Diagram) Design | 0.6 | Tran Hoang Tam | 0.6 | Done | 2020-03-04
[Review 03] Interface Design Annotation | 2 | Tran Hoang Tam | 2 | Done | 2020-03-04
[Review 02] Sequence Diagram Design |  | Tran Hoang Tam |  |  | 2020-04-04
Total | 64.75 |  | 102.3% |  | Done task: